## Sheet1
Focus Implementation - FY25 Work Plan
First Year Timeline, Responsibility
Strategic Directions | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2
| April through June | July through September | October through December | January through March | April through June
Optimizing Organizational Effectiveness | Board calendar w/ Board dates (Marcel) | Glossary (Kirsten)
| Engage grant specialist for compliance (Malcolm) | Grant writer for future grants (Malcolm)
| Update the budget (Michael, Malcolm, Accountant) | Contract with a fundraiser (Malcolm and Robin)
All board members go inside (Jay)
Identify missing Board member skill sets & diversity (Kirsten & Robin)
Growing Our Impact | Complete currriculum & facilitator handbook (Jay / Malcolm/Dave) |  | Develop & deliver advanced (3-4 day) facilitator training (Jay deliver in Q2 2026)
Develop & deliver a 1 day introductory facilitator training (Dave)
Job description for key staff (Malcolm/Robin)
Mobilizing Community Support & Engagement |  | Marketing & community strategy (TBD Board Member)
Build out database ( Fundraising/ Malcolm)
4 Groups in 3 facilities June - Q4 (Malcolm/Jay/Scott/Dave)
Website complete (Marcel/Malcolm)